## Slide 1
Science Ready Data Products -CoDR
Cost Model
Jeff Kern

## Slide 2
Cost Model Overview
SRDP Project is funded out of NRAO operations.
  Allocated resources are people not $
  Profile can be slowly varied but in general not fungible
    For instance, increase in number of DAs over time
    Controlled at observatory level.
DMS supporting SRDP through prioritization
  Re-allocation of existing staff effort
  Hardware part of overall observatory computing resources
    Annual upgrades, maintenance, growth

## Slide 3
Operations Plan
Why was an operations plan not presented?
Operations is built into the project from early on.
  Choice made to prevent organizational split
    ALMA / VLA
    Development / Ops
  Operations plan is … more of the same.
Uncertainties in operational model
SRDP-18
Capability
Efficiency
Uptake
Operations Plan
  VLASS Development
  ALMA Evolution
  QA Efficiency
  Automation Efficiency
  Community Uptake
  Data Quality Issues

## Slide 4
What About Operations Budget?
SRDP Operations begin as soon as the first capabilities are delivered.
SRDP-18
SRDP-77
SRDP-122
Includes: VLASS
Chart: Unburdened Labor Cost
| 43101 | 43466 | 43831 | 44197 | 44562 | 44927 | 45292
Project Office | 176 | 249 | 365 | 365 | 365 | 277 | 189
ALMA: Heu | 102 | 330 | 330 | 330 | 330 | 330 | 330
ALMA:Ops | 209 | 245 | 385 | 189 | 189 | 189 | 189
VLA:Heu | 0 | 51 | 127 | 127 | 127 | 127 | 127
VLA:Ops | 342 | 608 | 437 | 672 | 666 | 684 | 613
Staff In
Place
K$
Post-Project Operations

## Slide 5
Concerns about cost model
Concern: Are you budgeting enough resources for managing departmental interfaces?
  Benefit from high level support across observatory.
  Should be my responsibility, support in Lewis and Brian as required
Concern: Would dedicated SRDP resources be more efficient?
  We don’t think so:
    Standing up parallel structures would be expensive
    Transition to operations then difficult
    Specialized knowledge
Concern: Alarmed at lack of contingency…
  Unusual structure of the project, covered earlier?
Concern: Algorithmic development
  Two levels of development:
    Heuristics Group
    ARDG
SRDP-122
Not Covered Elsewhere

## Slide 6
Reference a Robust BoE
Concern: … that demonstrates that a project-level MVP can be developed and deployed within an agreed-upon timescale within the LoE constraints of the project
Project design is to achieve the maximum scope for the given resources.
  Development never really will end
Incremental delivery and value throughout waves.
At the Conceptual Level for this project defining a robust BoE is difficult.
  Too many uncertainties need to be addressed.
SRDP-130

## Slide 7
Strain on staff prior to new release
Concern: Document says level of staff is placed under “considerable strain” prior to releases and this should be addressed in the "staffing plan".
This remark was intended to accomplish two things:
  Remind us that careful management around the release of pipeline version is required.
  Designate that this is a minimum level of effort required.
    The current staffing plan for the VLA is below this level and I think more effort will need to applied to SRDP during release periods.
SRDP-75

## Slide 8
S/W Schedule Contingency Planning
We have two primary areas where schedule contingency is broadly considered:
Implementation
  Schedule contingency during development is held within DMS by scheduling workloads at 80% capacity, reserving one day a week for unplanned tasks
Operations
  Production of data products is generally not mission critical.
    Most work in operations can be delayed until resources and staff are available.
  Exception to this is Time Critical Observations.
    Staff and resources needed for Time Critical Observations are typically a small fraction of the whole
    Contingency is to grant priority on a case by case basis as needed.
SRDP-41

## Slide 9
DMS Resources
Concerns:
  Sufficiency of DMS resources
  Front loading of project resources
 | FY18 | FY19 | FY20 | Number of team members involved
ICC | 0.2 | 0.2 | 0.2 | 1
M&C | 0.25 | 0.25 | 0.25 | 1
SSA | 2.5 | 2.5 | 2.5 | 7
CASA | 3.5 | 3.5 | 3.5 | 11
HPC/Systems | 0.25 | 0.25 | 0.25 | 2
Architect | 0.5 | 0.5 | 0.5 | 2
Testing | 0.3 | 0.3 | 0.3 | 2
Sum | 7.5 | 7.5 | 7.5 | 26
These are our initial guesses based on experience with ALMA and VLASS, to be refined as we decompose the system concept into requirements
SRDP-46
SRDP-57
Table 3: DMS Project SRDP Budget (FTE's)
DMS effort lines up with effort available from SRDP, i.e. Project Scientist/Ops Mgr/DA’s
This represents ~60% of the available development time of CASA and SSA
We’ve only estimated the first 3 years. Over time SSA will probably ramp down, CASA likely to stay higher longer.
Notes: Estimation examples:
CASA – implementation of heuristics, and software infrastructure to support that
-> similar to ALMA calibration and imaging
SSA – extend the archive, workflow manager, reprocessing
-> similar to the new archive development and corresponding tasks in VLASS

## Slide 10
DMS Cost Plan
Concern: Is there a DMSD cost plan we can look at?
People
  Refer to DMS Resource Plan on previous slide
  Schedule at 80% to build in contingency
Hardware
  Hardware costs will be managed as part of the overall observatory hardware capabilities budget
  Ramp up slowly, so we don't shock the system
Hardware Contingency
  Discussed in SRDP-47
SRDP-149

## Slide 11
Architecture and Cost
Concerns:
  When will the architecture be complete?
  Architecture vs. service implementation
  Re-use of existing architecture
Architecture will be completed gradually as requirements decomposition and detailed design proceeds with each wave.
Much of our existing architecture will be re-used or extended, reducing cost vs. a “greenfield” project:
  CASA/Pipelines
  Archive
  Reprocessing
  VLASS Survey Status Database (Workflow Manager)
  Helpdesk
  Messaging/monitoring
Design and Integration processes will help develop the services, i.e. operational changes, needed for SRDP. This will involve both SRDP and DMS resources.
SRDP-124