## Slide 1
Science Ready Data Products Operations Review

## Slide 2
Summary
51 RIDs submitted by review team + Lewis Ball
36 set to “Done”
4 post-review actions
This presentation covers issues flagged as needing discussion.

## Slide 3
Science concerns
Issues relating to scientific staff effort and the evolution of SRDP capabilities
SRDP-285: Unrealistic/non-existent estimation of the role of the scientific staff in SRDP operations (A. Remijan)
SDRP-309: VLA feedback (C. Chandler)
SRDP-314: Clarify what will be covered in each wave (C. Chandler)
SRDP-321: definition of science quality (C. Chandler)

## Slide 4
SRDP-285
Unrealistic/non-existent estimation of the role of the scientific staff in SRDP operations
“The only place where scientist involvement is described in the operations plan is in WF2 in section 8.1. I think this grossly underestimates the role of the scientific staff in SRDP operations. Especially during the Pilot and Wave 1, support will be needed from the scientific staff in order to help in operations.”
Response (Section 6.3) – scientist effort added: Scientist effort to help with SRDP operations (for the data analysts to consult if they have questions about QA, and also for responding to user queries that lie beyond a DA’s expertise) is estimated at 10% of the DA effort (based on NA ALMA data processing operations). For the Pilot and Wave 1, scientist effort in Socorro has been identified, and the Operations Manager will provide science support in Charlottesville. Any further resource needs will be assessed at the review of Wave 1 operations.
Discussion:
10% based on ALMA NA data processing ops, realistic?
  SRDP will promise science quality imaging, so a higher bar.
  However, most scientist effort in NA data processing was for difficult manual data processing that SRDP will not attempt.
Scientist effort for SRDP in NM is assigned by the Head of SUS, in Charlottesville it is expected that the Operations Manager will provide the science support, at least initially.

## Slide 5
SRDP-309
VLA feedback
“It is not clear whose responsibility it is to attend the weekly Thursday meeting to provide feedback from the pipeline to the VLA observatory staff.”
Response: The head of Science User Support in Socorro collates feedback from the data analysts and presents any issues at these meetings.
Discussion
If the head of SUS is to represent SRDP at the weekly meetings this needs to be included in the required scistaff effort.
Will there be many more issues seen as a result of SRDP than are already caught in the first calibration run? Head of SUS already attends to report these.

## Slide 6
SRDP-314
Clarify what will be covered in each wave
“It was not at all clear what is to be covered in the different waves described. For example, where to spectroscopy and polarimetry for the VLA appear? Do these more complex observations require additional resources for the QA? The plan seems to assume that wave 2 = steady state, but I foresee considerable more effort needed unless a lot of automated QA is developed, which is not described.”
Response (abridged): SRDP operations will execute the pipeline capabilities in each Wave as they become available. The capabilities roadmap for the pipeline is yet to be developed, and will be the responsibility of the SRDP Project Scientist, with advice from the SRDP Stakeholders Committee. ….I agree we will need to be cautious that introducing new capabilities comes with improvements to the pipeline and weblog that ensure that QA does not become significantly more burdensome.
Discussion:
Feed back of concerns over QA difficulty into the SRDP pipeline capabilities roadmap.

## Slide 7
SRDP-321
Definition of science quality
“In section 8.1 the concept of a calibration or image being of "science quality" or a "scientifically-valid result" is introduced, but there is no mention of who or how the decision that something is of science quality is made. Nominally, I would think that this requires the input of a scientist, but as mentioned elsewhere, such resources have not been evaluated.”
Response: Scientist resources have now been added (Section 6.3).
Discussion: Who decides if a product is science ready? Does this need scientist effort?
We certainly need a clear set of QA standards that SRDP products will be held to, written by scientists (post-review action, SRDP-289).
Could implementation of those standards, once written, be left to DAs?

## Slide 8
Data analyst intervention in the workflows
SRDP-286: DA vs. user defined parameters (A. Remijan)
SRDP-284 - Inconsistency in WF3 and WF6 regarding user initiated optimized imaging and recalibration. (Marked as “done” pending this discussion.)

## Slide 9
SRDP-286
DA vs. user defined parameters
“It is described that the DAs will "suggest changes to the parameters if it is clear that doing so will improve the results." I find this in contradiction to WF3 and WF6 where the user has requested re-imaging or calibration. Wouldn't the user be the most informed on how the parameters should be changed to improve the results.”
Response: (ML) I still would like to keep this statement in here - many of our users will not necessarily be very experienced, and input from the DAs might be very valuable.
Meeting topic: (AR) I would like further discussion on this point as I feel there is a disconnect between normal DA operations and what SRDP would be asking the DAs to assess in the workflows.
Question for discussion: What should be the role (if any) of DAs in helping/advising users in the user-initiated imaging and calibration workflows?

## Slide 10
SRDP-297
Overview (A. Remijan)
“It should be clearly pointed out that the SRDP operations must not interfere with core deliverables to ALMA or the VLA when the division heads are allocating resources.”
Response (JK, abridged): The SRDP project doesn't set the overall priorities, that is done by the division head and the management chain above. I don't disagree with the concept, just that this is not the appropriate place to put it.
Discussion topic (AR): I understand that SRDP does not set the priorities but it does have its own deliverables (as do the sites) so what falls off the table if the necessary resources are not available?

## Slide 11
SRDP-303
Socorro Operations Lustre Estimates (J. Robnett)
“This section states 255TB will be needed for the pilot and Wave 1 for EVLA calibrations. That's more than VLASS uses for calibration and imaging and roughly 4x more than the baseline pipeline operations usage so I have a hard time understanding how it was arrived at.
There is no free usable space on the NM lustre so whatever delta SRDP will contribute needs to be accounted for. ”
Response (abridged):
This includes both pipeline runs and user restores, and assumes both hang around for about one month.
Implications:
As there is currently no space on Lustre, an additional 2 Lustre servers at $30k each will need to be ordered to support SRDP.
Mitigations (would roughly halve the request):
data cache for calibrated MSes (currently descoped for Pilot & W1 by SSA)
Shorten the hold time on disk to ~ 2 weeks (would impact user experience, particularly for those with poor network connections)

## Slide 12
SRDP-310
Meeting frequency (C. Chandler)
“From experience with VLASS operations, it is necessary to meet much more often than once a week for 30mins. When we start an observing campaign, we meet twice a day, and I imagine that the DAs would require and appreciate much more interaction than Jira tickets and a weekly meeting.”
Response (abridged): ML discussed this with Drew when he was last in Socorro, and Drew thought a weekly meeting was fine (with the ability to Skype etc for further impromptu meetings as needed).
Discussion “A Day in the Life of SRDP” (Wave 1)
NM: About 8 EBs per day for calibration, of which 4-6 will be SRDP compliant, 50% of these will need some attention (extra flagging etc) and rerunning.
  Expect 2-3 per week to need a scientist to examine them (particularly in the early days). Probably few enough in number to deal with in a weekly meeting+emails (may need to increase number of meetings though. Decide after pilot.)
Cville: About 2 jobs per day of optimized imaging.
  Expect only ~1/week to need scientist attention.
Other operations tasks:
  Metrics collection and reporting (once per week, with a major report out once per quarter).
  Managment of SRDP compute and storage resource use, and planning for the future.
  Reporting problems with telescopes, pipelines and archives
  Testing new versions of the SRDP software.
  Answering helpdesk questions about SRDP products and arranging for reprocessing, if necessary.
  Large project QA and ingest.

## Slide 13
SRDP-319
Remote processing recommendation (C. Chandler)
“In section 7.3, the idea is floated that non-NRAO resources may be trained in QA processes. Since none of these resources will be under NRAO control I highly recommend that this not be considered (at least, initially), otherwise we have no means of quality control.”
Response (abridged):The intention is that this would be part of the Radial project and that before handing the QA process over to someone external they would certainly need to be trained (and observed for a period).
Discussion: Does QA have to be done by an NRAO employee (or a closely related org. such as JAO), or will the training and supervision of remote DAs be sufficient? (Note that one of the motivations of the Radial program is to train students at HBCUs in radio astronomy, and having them take on some DA tasks would be effective at this, so this decision may be made at a higher level than the SRDP project.)

## Slide 15
SRDP-292
Section 5.1.4 - What is realfast?
“I must have missed a document but I don't see where "realfast" is defined in our current suite of documents to review.”
Response (abridged):Realfast, a commensal fast transient detection system for the VLA, will be operating by the start of the pilot. Ingest of realfast products into the archive are formally part of SRDP WF9 (large projects), though in practice the ingest will be managed by the realfast team. We expect minimal operational impact from this on the SRDP team.”
Discussion:
What is the role of SRDP in realfast?
  Part of the objective of SRDP is to have large projects return data to the archive.

## Slide 16
SRDP-283
Scope of testing
“Section 12.4 Capabilities that are initiated by a PI, or have explicit PI input, should be tested by sample PIs, not just by operations staff.”
Response (abridged): I think there are two aspects to this, heuristics testing, which should involve experienced ALMA and VLA PIs, and also operations testing, which should utilize accounts that only have user permissions to check that the user experience is as designed. Changes made to Sections 12.2:
...These tests will be conducted under the auspices of SRDP, and testing will be led by the Project Scientist or their designee. They will include PIs of ALMA and VLA projects. The user experience with the workflow will be included in the testing.
And 12.4:
...Tests will include use of accounts with only user permissions to verify that the user experience is as designed.